## Slide 1: Website Project Timeline City of Visionville, CA
User Experience
Monday, January 1st 2pm
[3 weeks after kickoff]
[Client-determined date here]
Project Kick Off
We will review the project scope, timeline , and overall process. We want to establish our working relationship as well as confirm your expectations and priorities for the project.
Discovery Materials Due
Completion of Discovery survey, comments added to comps via InVision app, and graphical assets added to the Box folder.
User Experience (UX) Presentation
We will discuss User Experience best practices, review Discovery materials and analytics data. Lastly, we will deliver and discuss homepage wireframe.
User Experience
User Experience
Graphic Design
[Day after UX Presentation]
[3 biz days after UX Presentation]
[Week after Wireframe Approval]
Graphic Design Workshop
An interactive session with your Art Director and Project Manager to review the proposed design and layout of your site.
Homepage Layout Approval
Return signed approval of homepage layout wireframe.
Homepage Delivery
Present and discuss initial homepage compositions via screenshare. Collect initial impressions and feedback on the Invision app.
Graphic Design
Graphic Design
Graphic Design
[Use date range in Wrike]
[Use date in Wrike]
[Use date range in Wrike]
Homepage Design Revision (Delete?)
Collect feedback left on Invision app & create new homepage comps. Recommended turn-around time is 2 business days to collect feedback & respond.
Homepage Approval
Return signed approval of homepage graphic design.
Interior Design & Revision (Maybe Delete?)
Repeat process of presentation & revision of homepage for the interior page compositions.
Graphic Design
Content Preparation
Content Preparation
[Use date in Wrike]
[Use date in Wrike]
[Use date in Wrike]
Graphic Design Approval
Finalize graphic design comps and return signed approval.
Proposed Sitemap Completed
Provide finished Proposed Sitemap for the new website information hierarchy.
User Access & Content Groups finalized
Provide finished User Access & Content Groups spreadsheet. This conveys which departments have access to certain components.
Content Preparation
Soft Launch
Soft Launch
[Use date in Wrike]
[Use date in Wrike]
[Use date range in Wrike]
Content Migration Templates Complete
Add Content Migration Templates to Box folder. Files should be organized in a manner that matches the Proposed Sitemap
New Website Development Complete
Deliver & provide access to front-end of new website once development and quality assurance have been completed.
User Acceptance Testing (UAT)
Website access is provided to client. Client has 10 business days to identify and document any website issues or changes to approved behaviors/appearances.
User Experience
User Experience
Soft Launch
[Use date(s) in Wrike]
CMS Training
Client is trained on using the CMS by a Vision technical trainer.
Soft Launch
[Use date range in Wrike]
Complete Content Updates
Client will make any remaining updates to their content before Go-Live.
Soft Launch
[Use date range in Wrike]
Transfer to Staging Environment
After UAT punchlist is resolved, website will be transferred to the staging/production URL. This version of the site will eventually be viewed by the public.
Content Preparation
Content Migration Complete
Content submitted for migration has been added to the new website.
[Use date in Wrike]
Go Live
[Use date in Wrike]
Schedule Live Date
Discuss any remaining preparations for Go-Live such as the new IP for DNS records, adjusting TTL settings, and a timetable for website launch.
Go Live
[Use date in Wrike]
Go Live
Client to update DNS records. Vision will finalize any CMS settings as well as perform search engine registration.
Content Preparation
Content Strategy
[Describe Content Strategy Offering:
Basic – single day, 1hr GoToMeeting
Standard – single day, onsite training
Plus – 2 days onsite]
[Use date(s) in Wrike]