## NewTemplate
|  |  | Home |  | Current Project Status: |  | Open | Last Updated: |  | 2016-01-01 |  |  |  | Last Completed: | 0
|  |  | Vision Place Holder Project Name |  | Project ID |  | vi101.1 | BMS | % | Amount | TMID | Completion |  | NPS Score | Sent on | Score
[5 empty] | Enter Start Date | >>>>>>> | 2016-01-01 | 1 | 40% | 20000 | 0-PP01N | 0 |  | GD PM | 0
|  |  | Notes: Update for each new project: 1. update successor task for Training Type 2. update the payment milestone completion as necessary Editing Comments in this cell 1. Enter notes & comments here. 2. F2 key puts this cell in Edit mode 3. "Alt+Enter" puts a new line |  | Estimated Go Live Date |  | 2016-08-31 | 2 | 20% | 10000 | 2a-GD05N | 0 |  | GD Vision | 0
[5 empty] | Project Type |  | New Site | 3 | 20% | 10000 | 2c-DV11N | 0 |  | Launch PM | 0
[5 empty] | Project Group ID |  | vi101 | 4 | 20% | 10000 | 4-GM04N | 0 |  | Launch Vision | 0
[5 empty] | Project Manager |  | PM1 | [6 empty] | Since Execution |  | weeks
[5 empty] | Training Type |  | WebEX or Onsite | [6 empty] | Since Kickoff | 0 | weeks
[5 empty] | Project Total |  | 50000 | [6 empty] | Kickoff to Launch | in progress | weeks
[5 empty] | Project % Completion |  | 0 | Total Invoiced: |  | 0 | Project $ | 50000 |  | Launch Date | 0
rFilter | TM Value Proportion | TM Value | Phase [ TM ID ] | Tasks/Milestones | Comments | Prede cessor | Enter Actual Completion Date | Add days [client delay time] | Add days [vision lead time] | Task/Milestone Start Date | Target Duration | Add Duration [vision] | Add Duration [Client] | Task/Milestone Target Completion Date | Gannt
| 8 | 1 | Assignment |  |  |  | 0% |  |  | 2016-01-01 |  |  |  | 2016-01-13 | 12
| 0.25 | 2 | 0-PP01N | Contract Execution |  | #N/A |  |  |  | 2016-01-01 | 2 |  |  | 2016-01-05 | 4
| 0.25 | 2 | 0-PP02N | Assign PM |  | #N/A |  |  |  | 2016-01-05 | 2 |  |  | 2016-01-07 | 2
| 0.375 | 3 | 0-PP03N | Internal Kickoff Meeting |  | #N/A |  |  |  | 2016-01-07 | 3 |  |  | 2016-01-12 | 5
| 0.125 | 1 | 0-PP04N | Client introduction email/call, schedule Kickoff call |  | #N/A |  |  |  | 2016-01-12 | 1 |  |  | 2016-01-13 | 1
| 66 | 15 | UX Consulting |  |  |  | 0% |  |  | 2016-01-12 |  |  |  | 2016-02-04 | 23
| 0.22727 | 1 | 1-UX01N | Set up Vision Network resources for project |  | #N/A |  |  |  | 2016-01-12 | 1 |  |  | 2016-01-13 | 1
| 0.22727 | 1 | 1-UX02N | Schedule site mapping with content migrator |  | #N/A |  |  |  | 2016-01-12 | 1 |  |  | 2016-01-13 | 1
| 1.3636 | 6 | 1-UX03N | Kickoff Call |  | #N/A |  |  | 5 | 2016-01-19 | 1 |  |  | 2016-01-20 | 1
| 0.45455 | 2 | 1-UX04N | Create ticket for UX specialist |  | #N/A |  |  | 1 | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 0.45455 | 2 | 1-UX05N | Deliver Kickoff call recap |  | #N/A |  |  | 1 | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 0.45455 | 2 | 1-UX06N | Deliver Discovery Package |  | #N/A |  |  | 1 | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 0.45455 | 2 | 1-UX07N | Install/get access to Google Analytics |  | #N/A |  |  | 1 | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 0.45455 | 2 | 1-UX08N | Install/get access to Heatmap |  | #N/A |  |  | 1 | 2016-01-21 | 1 |  |  | 2016-01-22 | 1
| 0.22727 | 1 | 1-UX09N | Schedule Consulting Workshop |  | #N/A |  |  |  | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 1.1364 | 5 | 1-UX10N | Site map current website |  | #N/A |  |  |  | 2016-01-13 | 5 |  |  | 2016-01-20 | 7
| 1.8182 | 8 | 1-UX11N | Review Discovery Package |  | #N/A |  |  | 7 | 2016-01-28 | 1 |  |  | 2016-01-29 | 1
| 1.1364 | 5 | 1-UX12N | Create Graphic Design Workshop Presentation Board |  | #N/A |  |  | 4 | 2016-02-03 | 1 |  |  | 2016-02-04 | 1
| 1.1364 | 5 | 1-UX13N | Create draft homepage layout wireframes |  | #N/A |  |  | 4 | 2016-02-03 | 1 |  |  | 2016-02-04 | 1
| 1.1364 | 5 | 1-UX14N | Get Production Team approval for wireframes |  | #N/A |  |  | 4 | 2016-02-03 | 1 |  |  | 2016-02-04 | 1
| 3.4091 | 15 | 1-UX15N | Consulting Workshop - Project & CMS Overview (WebEx or Onsite Meeting) |  | #N/A |  |  | 14 | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 0.22727 | 1 | 1-UX16N | Consulting Workshop - Wireframe (WebEx or Onsite Meeting) |  | #N/A |  |  |  | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 0.22727 | 1 | 1-UX17N | Consulting Workshop - Graphic Design (WebEx or Onsite Meeting) |  | #N/A |  |  |  | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 0.22727 | 1 | 1-UX18N | Homepage wireframe approval |  | #N/A |  |  |  | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 0.22727 | 1 | 1-UX19N | Content Strategy Workshop |  | #N/A |  |  |  | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 53 | 15 | Graphic Design |  |  |  | 0% |  |  | 2016-02-09 |  |  |  | 2016-05-20 | 101
| 0.28302 | 1 | 2a-GD01N | Create Mood Board |  | #N/A |  |  |  | 2016-02-09 | 1 |  |  | 2016-02-10 | 1
| 2.8302 | 10 | 2a-GD02N | Create homepage design concepts |  | #N/A |  |  | 7 | 2016-02-22 | 3 |  |  | 2016-02-25 | 3
| 0.28302 | 1 | 2a-GD03N | Homepage design review |  | #N/A |  |  |  | 2016-02-25 | 1 |  |  | 2016-02-26 | 1
| 0.28302 | 1 | 2a-GD04N | Present homepage design concepts |  | #N/A |  |  |  | 2016-02-26 | 1 |  |  | 2016-02-29 | 3
| 0.28302 | 1 | 2a-GD05N | Homepage Graphic Design delivery |  | #N/A |  |  |  | 2016-02-26 | 1 |  |  | 2016-02-29 | 3
| 4.2453 | 15 | 2a-GD06N | Homepage Graphic Design revision |  | #N/A |  |  |  | 2016-02-29 | 15 | 5 |  | 2016-03-28 | 28
| 0.28302 | 1 | 2a-GD07N | Homepage Graphic Design approval |  | #N/A |  | 15 |  | 2016-04-18 | 1 |  |  | 2016-04-19 | 1
| 1.4151 | 5 | 2a-GD08N | Create interior page & mobile design |  | #N/A |  |  | 3 | 2016-04-22 | 2 |  |  | 2016-04-26 | 4
| 0.28302 | 1 | 2a-GD09N | Interior page design review |  | #N/A |  |  |  | 2016-04-26 | 1 |  |  | 2016-04-27 | 1
| 0.28302 | 1 | 2a-GD10N | Present interior page design concepts |  | #N/A |  |  |  | 2016-04-27 | 1 |  |  | 2016-04-28 | 1
| 3.1132 | 11 | 2a-GD11N | Interior page design revision |  | #N/A |  |  | 5 | 2016-05-05 | 6 |  |  | 2016-05-13 | 8
| 0.84906 | 3 | 2a-GD12N | Interior page Graphic Design approval |  | #N/A |  |  |  | 2016-05-13 | 3 |  |  | 2016-05-18 | 5
| 0.28302 | 1 | 2a-GD13N | Graphic Design Signoff Document executed |  | #N/A |  |  |  | 2016-05-18 | 1 |  |  | 2016-05-19 | 1
| 0.28302 | 1 | 2a-GD14N | Send Graphic Design Client Satisfaction Survey |  | #N/A |  |  |  | 2016-05-19 | 1 |  |  | 2016-05-20 | 1
| 69 | 10 | Content Prep |  |  |  | 0% |  |  | 2016-02-04 |  |  |  | 2016-05-02 | 88
| 0.43478 | 3 | 2b-CP01N | Initialize blank site for content (if applicable) |  | #N/A |  |  |  | 2016-02-09 | 3 |  |  | 2016-02-12 | 3
| 0.72464 | 5 | 2b-CP02N | Create proposed Sitemap |  | #N/A |  |  | 4 | 2016-02-16 | 1 |  |  | 2016-02-17 | 1
| 0.28986 | 2 | 2b-CP03N | Deliver proposed Sitemap |  | #N/A |  |  | 1 | 2016-02-18 | 1 |  |  | 2016-02-19 | 1
| 0.72464 | 5 | 2b-CP04N | Sitemap approval / Content Groups Finalized |  | #N/A |  |  |  | 2016-02-19 | 5 |  |  | 2016-02-26 | 7
| 0.14493 | 1 | 2b-CP05N | Schedule Content Migration |  | #N/A |  |  |  | 2016-02-26 | 1 |  |  | 2016-02-29 | 3
| 6.5217 | 45 | 2b-CP06N | Begin Content Migration |  | #N/A |  |  |  | 2016-02-29 | 45 |  |  | 2016-05-02 | 63
| 0.14493 | 1 | 2b-CP07N | Send Approval Cycle Worksheet |  | #N/A |  |  |  | 2016-02-26 | 1 |  |  | 2016-02-29 | 3
| 1.0145 | 7 | 2b-CP08N | Approval Cycle Worksheet approval, including user details |  | #N/A |  |  |  | 2016-02-29 | 7 |  |  | 2016-03-09 | 9
| 64 | 30 | Development |  |  |  | 0% |  |  | 2016-05-02 |  |  |  | 2016-08-01 | 91
| 0.46875 | 1 | 2c-DV01N | Prepare programming specifications |  | #N/A |  |  |  | 2016-05-19 | 1 |  |  | 2016-05-20 | 1
| 0.46875 | 1 | 2c-DV02N | Submit BTNET ticket to programming |  | #N/A |  |  |  | 2016-05-19 | 1 |  |  | 2016-05-20 | 1
| 2.3438 | 5 | 2c-DV03N | Get access credentials for client's hosting environment (if applicable) |  | #N/A |  |  |  | 2016-05-19 | 5 |  |  | 2016-05-26 | 7
| 2.3438 | 5 | 2c-DV04N | Verify client's hosting environment meets requirements (if applicable) |  | #N/A |  |  |  | 2016-05-19 | 5 |  |  | 2016-05-26 | 7
| 9.375 | 20 | 2c-DV05N | Frontend Development |  | #N/A |  |  | 10 | 2016-06-03 | 10 |  |  | 2016-06-17 | 14
| 7.0312 | 15 | 2c-DV06N | Backend Development |  | #N/A |  |  | 5 | 2016-06-24 | 10 |  |  | 2016-07-11 | 17
| 0.46875 | 1 | 2c-DV07N | Schedule QA Task |  | #N/A |  |  |  | 2016-07-11 | 1 |  |  | 2016-07-12 | 1
| 0.46875 | 1 | 2c-DV08N | Schedule training sessions |  | #N/A |  |  |  | 2016-07-12 | 1 |  |  | 2016-07-13 | 1
| 2.3438 | 5 | 2c-DV09N | Quality assurance test |  | #N/A |  |  |  | 2016-07-12 | 5 |  |  | 2016-07-19 | 7
| 3.75 | 8 | 2c-DV10N | Quality assurance revision |  | #N/A |  |  |  | 2016-07-19 | 8 |  |  | 2016-07-29 | 10
| 0.46875 | 1 | 2c-DV11N | Prototype website implementation on development server |  | #N/A |  |  |  | 2016-07-29 | 1 |  |  | 2016-08-01 | 3
| 0.46875 | 1 | 2c-DV12N | Complete Content Migration |  | #N/A |  |  |  | 2016-05-02 | 1 |  |  | 2016-05-03 | 1
| 108 | 15 | Soft Launch |  |  |  | 0% |  |  | 2016-08-01 |  |  |  | 2016-09-14 | 44
| 0.13889 | 1 | 3-SL01N | Schedule site transfer to production environment (vision or client) |  | #N/A |  |  |  | 2016-08-01 | 1 |  |  | 2016-08-02 | 1
| 0.97222 | 7 | 3-SL02N | Transfer and set up production website |  | #N/A |  |  | 5 | 2016-08-09 | 2 |  |  | 2016-08-11 | 2
| 0.13889 | 1 | 3-SL03N | Conduct New Site Configuration checklist |  | #N/A |  |  |  | 2016-08-11 | 1 |  |  | 2016-08-12 | 1
| 0.13889 | 1 | 3-SL04N | Conduct QA launch checklist items |  | #N/A |  |  |  | 2016-08-12 | 1 |  |  | 2016-08-15 | 3
| 3.6111 | 26 | 3-SL05N | Training session 1 (3 hour WebEx) if applicable |  | #N/A |  |  | 25 | 2016-08-16 | 1 |  |  | 2016-08-17 | 1
| 3.6111 | 26 | 3-SL06N | Training session 2 (3 hour WebEx) if applicable |  | #N/A |  |  | 25 | 2016-08-16 | 1 |  |  | 2016-08-17 | 1
| 3.6111 | 26 | 3-SL07N | Onsite Training (if applicable) |  | #N/A |  |  | 25 | 2016-08-16 | 1 |  |  | 2016-08-17 | 1
| 0.13889 | 1 | 3-SL08N | Introduce CMS Support Team |  | #N/A |  |  |  | 2016-08-17 | 1 |  |  | 2016-08-18 | 1
| 0.13889 | 1 | 3-SL09N | UAT - Compile Punchlist items and/or Addendum |  | #N/A |  |  |  | 2016-08-18 | 1 |  |  | 2016-08-19 | 1
| 0.13889 | 1 | 3-SL10N | UAT - Punchlist items and/or Addendum client sign-off |  | #N/A |  |  |  | 2016-08-19 | 1 |  |  | 2016-08-22 | 3
| 1.3889 | 10 | 3-SL11N | UAT - Complete Punchlist/Addendum work |  | #N/A |  |  |  | 2016-08-22 | 10 |  |  | 2016-09-06 | 15
| 0.69444 | 5 | 3-SL12N | UAT - Client sign-off on Punchlist/Addendum work is complete |  | #N/A |  |  |  | 2016-09-06 | 5 |  |  | 2016-09-13 | 7
| 0.13889 | 1 | 3-SL13N | Launch checklist |  | #N/A |  |  |  | 2016-09-13 | 1 |  |  | 2016-09-14 | 1
| 0.13889 | 1 | 3-SL14N | Deliver Client launch checklist |  | #N/A |  |  |  | 2016-08-17 | 1 |  |  | 2016-08-18 | 1
| 21 | 14 | Go-Live & Maint. |  |  |  | 0% |  |  | 2016-08-17 |  |  |  | 2016-09-14 | 28
| 0.66667 | 1 | 4-GM01N | Schedule Go-live date |  | #N/A |  |  |  | 2016-08-17 | 1 |  |  | 2016-08-18 | 1
| 0.66667 | 1 | 4-GM02N | Introduce Tech Support as primary point of contact |  | #N/A |  |  |  | 2016-09-13 | 1 |  |  | 2016-09-14 | 1
| 6.6667 | 10 | 4-GM03N | Client performs any additional content work |  | #N/A |  |  |  | 2016-08-17 | 10 |  |  | 2016-08-31 | 14
| 0.66667 | 1 | 4-GM04N | DNS redirect and Go-Live |  | #N/A |  |  |  | 2016-08-31 | 1 |  |  | 2016-09-01 | 1
| 0.66667 | 1 | 4-GM05N | Go-Live checklist |  | #N/A |  |  |  | 2016-09-01 | 1 |  |  | 2016-09-02 | 1
| 3.3333 | 5 | 4-GM06N | Send Launch Client Satisfaction survey |  | #N/A |  |  |  | 2016-09-01 | 5 |  |  | 2016-09-09 | 8
| 0.66667 | 1 | 4-GM07N | Send project launch email |  | #N/A |  |  |  | 2016-09-09 | 1 |  |  | 2016-09-12 | 3
| 0.66667 | 1 | 4-GM08N | Review project |  | #N/A |  |  |  | 2016-09-12 | 1 |  |  | 2016-09-13 | 1
Brand Colors
56.31.107
119.193.227
255.153.0
Secondary Colors
255.207.30
83.86.90
200.201.199
Tertiary Colors
142.130.190
186.174.214
Formulas:
Amount = MIN([Amount, row below]:K32)
NPS Score = MAX([NPS Score, row below]:O17)
Note on I2: Jung Yoon: Billing Milestone Number
Note on H8: Jung Yoon: update Task (4-GM03N) "Client performs any additional content work"
Note on K93: Jung Yoon: change predessor to proper training type Start Date

## UpgradeTemplate
|  |  | Home |  | Current Project Status: |  | Open | Last Updated: |  | 2016-01-01 |  |  |  | Last Completed: | 0
|  |  | Vision Place Holder Upgrade Project Name |  | Project ID |  | vi102.1 | BMS | % | Amount | TMID | Completion |  | NPS Score | Sent on | Score
[5 empty] | Enter Start Date | >>>>>>> | 2016-01-01 | 1 | 40% | 12000 | 0-PP01U | 0 |  | GD PM | 0
|  |  | Notes: Update for each new project: 1. update successor task for Training Type 2. update the payment milestone completion as necessary Editing Comments in this cell 1. Enter notes & comments here. 2. F2 key puts this cell in Edit mode 3. "Alt+Enter" puts a new line |  | Estimated Go Live Date |  | 2016-08-31 | 2 | 20% | 6000 | 2a-GD05U | 0 |  | GD Vision | 0
[5 empty] | Project Type |  | Upgrade | 3 | 20% | 6000 | 2c-DV11U | 0 |  | Launch PM | 0
[5 empty] | Project Group ID |  | vi102 | 4 | 20% | 6000 | 4-GM04U | 0 |  | Launch Vision | 0
[5 empty] | Project Manager |  | PM2 | [6 empty] | Since Execution |  | weeks
[5 empty] | Training Type |  | WebEX or Onsite | [6 empty] | Since Kickoff | 0 | weeks
[5 empty] | Project Total |  | 30000 | [6 empty] | Kickoff to Launch | in progress | weeks
[5 empty] | Project % Completion |  | 0 | Total Invoiced: |  | 0 | Project $ | 30000 |  | Launch Date | 0
rFilter | TM Value Proportion | TM Value | Phase [ TM ID ] | Tasks/Milestones | Comments | Prede cessor | Enter Actual Completion Date | Add days [client delay time] | Add days [vision lead time] | Task/Milestone Start Date | Target Duration | Add Duration [vision] | Add Duration [Client] | Task/Milestone Target Completion Date | Gannt
| 8 | 1 | Assignment |  |  |  | 0% |  |  | 2016-01-01 |  |  |  | 2016-01-13 | 12
| 0.25 | 2 | 0-PP01U | Contract Execution |  | #N/A |  |  |  | 2016-01-01 | 2 |  |  | 2016-01-05 | 4
| 0.25 | 2 | 0-PP02U | Assign PM |  | #N/A |  |  |  | 2016-01-05 | 2 |  |  | 2016-01-07 | 2
| 0.375 | 3 | 0-PP03U | Internal Kickoff Meeting |  | #N/A |  |  |  | 2016-01-07 | 3 |  |  | 2016-01-12 | 5
| 0.125 | 1 | 0-PP04U | Client introduction email/call, schedule Kickoff call |  | #N/A |  |  |  | 2016-01-12 | 1 |  |  | 2016-01-13 | 1
| 60 | 15 | UX Consulting |  |  |  | 0% |  |  | 2016-01-12 |  |  |  | 2016-02-04 | 23
| 0.25 | 1 | 1-UX01U | Set up Vision Network resources for project |  | #N/A |  |  |  | 2016-01-12 | 1 |  |  | 2016-01-13 | 1
| 1.5 | 6 | 1-UX03U | Kickoff Call |  | #N/A |  |  | 5 | 2016-01-19 | 1 |  |  | 2016-01-20 | 1
| 0.5 | 2 | 1-UX04U | Create ticket for UX specialist |  | #N/A |  |  | 1 | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 0.5 | 2 | 1-UX05U | Deliver Kickoff call recap |  | #N/A |  |  | 1 | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 0.5 | 2 | 1-UX06U | Deliver Discovery Package |  | #N/A |  |  | 1 | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 0.5 | 2 | 1-UX07U | Install/get access to Google Analytics |  | #N/A |  |  | 1 | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 0.5 | 2 | 1-UX08U | Install/get access to Heatmap |  | #N/A |  |  | 1 | 2016-01-21 | 1 |  |  | 2016-01-22 | 1
| 0.25 | 1 | 1-UX09U | Schedule Consulting Workshop |  | #N/A |  |  |  | 2016-01-20 | 1 |  |  | 2016-01-21 | 1
| 2 | 8 | 1-UX11U | Review Discovery Package |  | #N/A |  |  | 7 | 2016-01-28 | 1 |  |  | 2016-01-29 | 1
| 1.25 | 5 | 1-UX12U | Create Graphic Design Workshop Presentation Board |  | #N/A |  |  | 4 | 2016-02-03 | 1 |  |  | 2016-02-04 | 1
| 1.25 | 5 | 1-UX13U | Create draft homepage layout wireframes |  | #N/A |  |  | 4 | 2016-02-03 | 1 |  |  | 2016-02-04 | 1
| 1.25 | 5 | 1-UX14U | Get Production Team approval for wireframes |  | #N/A |  |  | 4 | 2016-02-03 | 1 |  |  | 2016-02-04 | 1
| 3.75 | 15 | 1-UX15U | Consulting Workshop - Project & CMS Overview (WebEx or Onsite Meeting) |  | #N/A |  |  | 14 | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 0.25 | 1 | 1-UX16U | Consulting Workshop - Wireframe (WebEx or Onsite Meeting) |  | #N/A |  |  |  | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 0.25 | 1 | 1-UX17U | Consulting Workshop - Graphic Design (WebEx or Onsite Meeting) |  | #N/A |  |  |  | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 0.25 | 1 | 1-UX18U | Homepage wireframe approval |  | #N/A |  |  |  | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 0.25 | 1 | 1-UX19U | Content Strategy Workshop |  | #N/A |  |  |  | 2016-02-08 | 1 |  |  | 2016-02-09 | 1
| 53 | 15 | Graphic Design |  |  |  | 0% |  |  | 2016-02-09 |  |  |  | 2016-05-20 | 101
| 0.28302 | 1 | 2a-GD01U | Create Mood Board |  | #N/A |  |  |  | 2016-02-09 | 1 |  |  | 2016-02-10 | 1
| 2.8302 | 10 | 2a-GD02U | Create homepage design concepts |  | #N/A |  |  | 7 | 2016-02-22 | 3 |  |  | 2016-02-25 | 3
| 0.28302 | 1 | 2a-GD03U | Homepage design review |  | #N/A |  |  |  | 2016-02-25 | 1 |  |  | 2016-02-26 | 1
| 0.28302 | 1 | 2a-GD04U | Present homepage design concepts |  | #N/A |  |  |  | 2016-02-26 | 1 |  |  | 2016-02-29 | 3
| 0.28302 | 1 | 2a-GD05U | Homepage Graphic Design delivery |  | #N/A |  |  |  | 2016-02-26 | 1 |  |  | 2016-02-29 | 3
| 4.2453 | 15 | 2a-GD06U | Homepage Graphic Design revision |  | #N/A |  |  |  | 2016-02-29 | 15 | 5 |  | 2016-03-28 | 28
| 0.28302 | 1 | 2a-GD07U | Homepage Graphic Design approval |  | #N/A |  | 15 |  | 2016-04-18 | 1 |  |  | 2016-04-19 | 1
| 1.4151 | 5 | 2a-GD08U | Create interior page & mobile design |  | #N/A |  |  | 3 | 2016-04-22 | 2 |  |  | 2016-04-26 | 4
| 0.28302 | 1 | 2a-GD09U | Interior page design review |  | #N/A |  |  |  | 2016-04-26 | 1 |  |  | 2016-04-27 | 1
| 0.28302 | 1 | 2a-GD10U | Present interior page design concepts |  | #N/A |  |  |  | 2016-04-27 | 1 |  |  | 2016-04-28 | 1
| 3.1132 | 11 | 2a-GD11U | Interior page design revision |  | #N/A |  |  | 5 | 2016-05-05 | 6 |  |  | 2016-05-13 | 8
| 0.84906 | 3 | 2a-GD12U | Interior page Graphic Design approval |  | #N/A |  |  |  | 2016-05-13 | 3 |  |  | 2016-05-18 | 5
| 0.28302 | 1 | 2a-GD13U | Graphic Design Signoff Document executed |  | #N/A |  |  |  | 2016-05-18 | 1 |  |  | 2016-05-19 | 1
| 0.28302 | 1 | 2a-GD14U | Send Graphic Design Client Satisfaction Survey |  | #N/A |  |  |  | 2016-05-19 | 1 |  |  | 2016-05-20 | 1
| 13 | 10 | Content Prep |  |  |  | 0% |  |  | 2016-02-04 |  |  |  | 2016-02-29 | 25
| 0.76923 | 1 | 2b-CP01U | Schedule site mapping with content migrator (if applicable) |  | #N/A |  |  |  | 2016-01-12 | 1 |  |  | 2016-01-13 | 1
| 3.8462 | 5 | 2b-CP02U | Site map current website (if applicable) |  | #N/A |  |  |  | 2016-01-20 | 5 |  |  | 2016-01-27 | 7
| 3.8462 | 5 | 2b-CP03U | Create proposed Sitemap (if applicable) |  | #N/A |  |  | 4 | 2016-02-16 | 1 |  |  | 2016-02-17 | 1
| 1.5385 | 2 | 2b-CP04U | Deliver proposed Sitemap (if applicable) |  | #N/A |  |  | 1 | 2016-02-18 | 1 |  |  | 2016-02-19 | 1
| 3.8462 | 5 | 2b-CP05U | Approval Cycle Worksheet (if applicable) |  | #N/A |  |  |  | 2016-02-19 | 5 |  |  | 2016-02-26 | 7
| 0.76923 | 1 | 2b-CP06U | Sitemap approval |  | #N/A |  |  |  | 2016-02-26 | 1 |  |  | 2016-02-29 | 3
| 64 | 30 | Development |  |  |  | 0% |  |  | 2016-05-19 |  |  |  | 2016-08-10 | 83
| 0.46875 | 1 | 2c-DV01U | Prepare programming specifications |  | #N/A |  |  |  | 2016-05-19 | 1 |  |  | 2016-05-20 | 1
| 0.46875 | 1 | 2c-DV02U | Submit BTNET ticket to programming |  | #N/A |  |  |  | 2016-05-19 | 1 |  |  | 2016-05-20 | 1
| 2.3438 | 5 | 2c-DV03U | Get access credentials for client's hosting environment (if applicable) |  | #N/A |  |  |  | 2016-05-19 | 5 |  |  | 2016-05-26 | 7
| 2.3438 | 5 | 2c-DV04U | Verify client's hosting environment meets requirements (if applicable) |  | #N/A |  |  |  | 2016-05-19 | 5 |  |  | 2016-05-26 | 7
| 9.375 | 20 | 2c-DV05U | Frontend Development |  | #N/A |  |  | 10 | 2016-06-03 | 10 |  |  | 2016-06-17 | 14
| 7.0312 | 15 | 2c-DV06U | Backend Development |  | #N/A |  |  | 5 | 2016-06-24 | 10 |  |  | 2016-07-11 | 17
| 0.46875 | 1 | 2c-DV07U | Schedule QA Task |  | #N/A |  |  |  | 2016-07-11 | 1 |  |  | 2016-07-12 | 1
| 0.46875 | 1 | 2c-DV08U | Schedule training sessions |  | #N/A |  |  |  | 2016-07-12 | 1 |  |  | 2016-07-13 | 1
| 2.3438 | 5 | 2c-DV09U | Quality assurance test |  | #N/A |  |  |  | 2016-07-12 | 5 |  |  | 2016-07-19 | 7
| 3.75 | 8 | 2c-DV10U | Quality assurance revision |  | #N/A |  |  |  | 2016-07-19 | 8 |  |  | 2016-07-29 | 10
| 0.46875 | 1 | 2c-DV11U | Prototype website implementation on development server |  | #N/A |  |  |  | 2016-07-29 | 1 |  |  | 2016-08-01 | 3
| 0.46875 | 1 | 2c-DV12U | Schedule scripted content migration |  | #N/A |  |  |  | 2016-08-01 | 1 |  |  | 2016-08-02 | 1
| 1.875 | 4 | 2c-DV13U | Perform scripted content migration |  | #N/A |  |  | 2 | 2016-08-04 | 2 |  |  | 2016-08-08 | 4
| 0.46875 | 1 | 2c-DV14U | Perform manual updates according to Sitemap (if applicable) |  | #N/A |  |  |  | 2016-08-08 | 1 |  |  | 2016-08-09 | 1
| 0.46875 | 1 | 2c-DV15U | Conduct post scripted content migration to-do list |  | #N/A |  |  |  | 2016-08-09 | 1 |  |  | 2016-08-10 | 1
| 108 | 15 | Soft Launch |  |  |  | 0% |  |  | 2016-08-10 |  |  |  | 2016-09-14 | 35
| 0.13889 | 1 | 3-SL01U | Schedule site transfer to production environment (vision or client) |  | #N/A |  |  |  | 2016-08-10 | 1 |  |  | 2016-08-11 | 1
| 0.97222 | 7 | 3-SL02U | Transfer and set up production website |  | #N/A |  |  | 5 | 2016-08-18 | 2 |  |  | 2016-08-22 | 4
| 0.13889 | 1 | 3-SL03U | Conduct Upgrade Site Configuration checklist |  | #N/A |  |  |  | 2016-08-22 | 1 |  |  | 2016-08-23 | 1
| 0.13889 | 1 | 3-SL04U | Conduct post-transfer QA launch checklist items |  | #N/A |  |  |  | 2016-08-23 | 1 |  |  | 2016-08-24 | 1
| 3.6111 | 26 | 3-SL05U | Training session 1 (3 hour WebEx) if applicable |  | #N/A |  |  | 25 | 2016-08-16 | 1 |  |  | 2016-08-17 | 1
| 3.6111 | 26 | 3-SL06U | Training session 2 (3 hour WebEx) if applicable |  | #N/A |  |  | 25 | 2016-08-16 | 1 |  |  | 2016-08-17 | 1
| 3.6111 | 26 | 3-SL07U | Onsite Training (if applicable) |  | #N/A |  |  | 25 | 2016-08-16 | 1 |  |  | 2016-08-17 | 1
| 0.13889 | 1 | 3-SL08U | Introduce CMS Support Team |  | #N/A |  |  |  | 2016-08-17 | 1 |  |  | 2016-08-18 | 1
| 0.13889 | 1 | 3-SL09U | UAT - Compile Punchlist items and/or Addendum |  | #N/A |  |  |  | 2016-08-18 | 1 |  |  | 2016-08-19 | 1
| 0.13889 | 1 | 3-SL10U | UAT - Punchlist items and/or Addendum client sign-off |  | #N/A |  |  |  | 2016-08-19 | 1 |  |  | 2016-08-22 | 3
| 1.3889 | 10 | 3-SL11U | UAT - Complete Punchlist/Addendum work |  | #N/A |  |  |  | 2016-08-22 | 10 |  |  | 2016-09-06 | 15
| 0.69444 | 5 | 3-SL12U | UAT - Client sign-off on Punchlist/Addendum work is complete |  | #N/A |  |  |  | 2016-09-06 | 5 |  |  | 2016-09-13 | 7
| 0.13889 | 1 | 3-SL13U | Launch checklist |  | #N/A |  |  |  | 2016-09-13 | 1 |  |  | 2016-09-14 | 1
| 0.13889 | 1 | 3-SL14U | Deliver Client launch checklist |  | #N/A |  |  |  | 2016-08-17 | 1 |  |  | 2016-08-18 | 1
| 21 | 14 | Go-Live & Maint. |  |  |  | 0% |  |  | 2016-08-17 |  |  |  | 2016-09-14 | 28
| 0.66667 | 1 | 4-GM01U | Schedule Go-live date |  | #N/A |  |  |  | 2016-08-17 | 1 |  |  | 2016-08-18 | 1
| 0.66667 | 1 | 4-GM02U | Introduce Tech Support as primary point of contact |  | #N/A |  |  |  | 2016-09-13 | 1 |  |  | 2016-09-14 | 1
| 6.6667 | 10 | 4-GM03U | Client performs any additional content work |  | #N/A |  |  |  | 2016-08-17 | 10 |  |  | 2016-08-31 | 14
| 0.66667 | 1 | 4-GM04U | DNS redirect and Go-Live |  | #N/A |  |  |  | 2016-08-31 | 1 |  |  | 2016-09-01 | 1
| 0.66667 | 1 | 4-GM05U | Go-Live checklist |  | #N/A |  |  |  | 2016-09-01 | 1 |  |  | 2016-09-02 | 1
| 3.3333 | 5 | 4-GM06U | Send Launch Client Satisfaction survey |  | #N/A |  |  |  | 2016-09-01 | 5 |  |  | 2016-09-09 | 8
| 0.66667 | 1 | 4-GM07U | Send project launch email |  | #N/A |  |  |  | 2016-09-09 | 1 |  |  | 2016-09-12 | 3
| 0.66667 | 1 | 4-GM08U | Review project |  | #N/A |  |  |  | 2016-09-12 | 1 |  |  | 2016-09-13 | 1
Formulas:
Amount = MIN([Amount, row below]:K30)
NPS Score = MAX([NPS Score, row below]:O17)
Note on I2: Jung Yoon: Billing Milestone Number
Note on H8: Jung Yoon: update Task (4-GM03U) "Client performs any additional content work"
Note on K92: Jung Yoon: change predessor to proper training type Start Date

## Data
visionHolidays |  | TMID | Task/Milestone
New Year's Day | 2016-01-01 | 0-PP01 | Contract Execution
Presidents’ Day | 2016-02-15 | 0-PP02 | Assign PM
Memorial Day | 2016-05-30 | 0-PP03 | Internal Kickoff Meeting
Independence Day | 2016-07-04 | 0-PP04 | Client introduction email/call, schedule Kickoff call
Labor Day | 2016-09-05 | 1-UX01 | Set up Vision Network resources for project
Thanksgiving | 2016-11-24 | 1-UX02N | Schedule site mapping with content migrator
Friday after Thanksgiving | 2016-11-25 | 1-UX03 | Kickoff Call
Christmas Eve Observed | 2016-12-23 | 1-UX04 | Create ticket for UX specialist
Christmas Observed | 2016-12-26 | 1-UX05 | Deliver Kickoff call recap
New Year’s Eve Observed | 2016-12-30 | 1-UX06 | Deliver Discovery Package
New Year's Day Observed | 2017-01-02 | 1-UX07 | Install/get access to Google Analytics
Presidents’ Day | 2017-02-20 | 1-UX08 | Install/get access to Heatmap
Memorial Day | 2017-05-29 | 1-UX09 | Schedule Consulting Workshop
Independence Day | 2017-07-04 | 1-UX10N | Site map current website
Labor Day | 2017-09-04 | 1-UX11 | Review Discovery Package
Thanksgiving | 2017-11-23 | 1-UX12 | Create Graphic Design Workshop Presentation Board
Friday after Thanksgiving | 2017-11-24 | 1-UX13 | Create draft homepage layout wireframes
Christmas Eve Observed | 2017-12-22 | 1-UX14 | Get Production Team approval for wireframes
Christmas Observed | 2017-12-26 | 1-UX15 | Consulting Workshop - Project & CMS Overview (WebEx or Onsite Meeting)
|  | 1-UX16 | Consulting Workshop - Wireframe (WebEx or Onsite Meeting)
|  | 1-UX17 | Consulting Workshop - Graphic Design (WebEx or Onsite Meeting)
|  | 1-UX18 | Homepage wireframe approval
|  | 1-UX19 | Content Strategy Workshop
|  | 2a-GD01 | Create Mood Board
|  | 2a-GD02 | Create homepage design concepts
|  | 2a-GD03 | Homepage design review
|  | 2a-GD04 | Present homepage design concepts
|  | 2a-GD05 | Homepage Graphic Design delivery
|  | 2a-GD06 | Homepage Graphic Design revision
|  | 2a-GD07 | Homepage Graphic Design approval
|  | 2a-GD08 | Create interior page & mobile design
|  | 2a-GD09 | Interior page design review
|  | 2a-GD10 | Present interior page design concepts
|  | 2a-GD11 | Interior page design revision
|  | 2a-GD12 | Interior page Graphic Design approval
|  | 2a-GD13 | Graphic Design Signoff Document executed
|  | 2a-GD14 | Send Graphic Design Client Satisfaction Survey
|  | 2b-CP01N | Initialize blank site for content (if applicable)
|  | 2b-CP01U | Schedule site mapping with content migrator (if applicable)
|  | 2b-CP02U | Site map current website (if applicable)
|  | 2b-CP02N | Create proposed Sitemap
|  | 2b-CP03N | Deliver proposed Sitemap
|  | 2b-CP03U | Create proposed Sitemap (if applicable)
|  | 2b-CP04U | Deliver proposed Sitemap (if applicable)
|  | 2b-CP05U | Approval Cycle Worksheet (if applicable)
|  | 2b-CP06U | Sitemap approval
|  | 2b-CP04N | Sitemap approval / Content Groups Finalized
|  | 2b-CP05N | Schedule Content Migration
|  | 2b-CP06N | Begin Content Migration
|  | 2b-CP07N | Send Approval Cycle Worksheet
|  | 2b-CP08N | Approval Cycle Worksheet approval, including user details
|  | 2c-DV01 | Prepare programming specifications
|  | 2c-DV02 | Submit BTNET ticket to programming
|  | 2c-DV03 | Get access credentials for client's hosting environment (if applicable)
|  | 2c-DV04 | Verify client's hosting environment meets requirements (if applicable)
|  | 2c-DV05 | Frontend Development
|  | 2c-DV06 | Backend Development
|  | 2c-DV07 | Schedule QA Task
|  | 2c-DV08 | Schedule training sessions
|  | 2c-DV09 | Quality assurance test
|  | 2c-DV10 | Quality assurance revision
|  | 2c-DV11 | Prototype website implementation on development server
|  | 2c-DV12N | Complete Content Migration
|  | 2c-DV12U | Schedule scripted content migration
|  | 2c-DV13U | Perform scripted content migration
|  | 2c-DV14U | Perform manual updates according to Sitemap (if applicable)
|  | 2c-DV15U | Conduct post scripted content migration to-do list
|  | 3-SL01 | Schedule site transfer to production environment (vision or client)
|  | 3-SL02 | Transfer and set up production website
|  | 3-SL03N | Conduct New Site Configuration checklist
|  | 3-SL04N | Conduct QA launch checklist items
|  | 3-SL03U | Conduct Upgrade Site Configuration checklist
|  | 3-SL04U | Conduct post-transfer QA launch checklist items
|  | 3-SL05 | Training session 1 (3 hour WebEx) if applicable
|  | 3-SL06 | Training session 2 (3 hour WebEx) if applicable
|  | 3-SL07 | Onsite Training (if applicable)
|  | 3-SL08 | Introduce CMS Support Team
|  | 3-SL09 | UAT - Compile Punchlist items and/or Addendum
|  | 3-SL10 | UAT - Punchlist items and/or Addendum client sign-off
|  | 3-SL11 | UAT - Complete Punchlist/Addendum work
|  | 3-SL12 | UAT - Client sign-off on Punchlist/Addendum work is complete
|  | 3-SL13 | Launch checklist
|  | 3-SL14 | Deliver Client launch checklist
|  | 4-GM01 | Schedule Go-live date
|  | 4-GM02 | Introduce Tech Support as primary point of contact
|  | 4-GM03 | Client performs any additional content work
|  | 4-GM04 | DNS Update and Go-Live
|  | 4-GM05 | Go-Live checklist
|  | 4-GM06 | Send Launch Client Satisfaction survey
|  | 4-GM07 | Send project launch email
|  | 4-GM08 | Review project
Note on F21: Jung Yoon: 1) Review Upgrade Consulting Checklist prior to meeting and go over all applicable items a 2) Update the "Upgrade Consulting Checklist" with information collected during and after the meeting
Note on F72: Jung Yoon: Add user accounts and set up approval cycles here.