## Sheet1
Done? | QA Test Script
Desktop
Review the responsive new site in a mobile device for glaring/obvious visual errors.
Review and update System Variables as necessary (this list will change as new features are added and DEV's may not have the information you have)
Test the “Splash Page Manager” and report any anomalies.
Check Feedback form
Check Print link
404 page formatting
Check SSO registration confirmation page formatting
Review Homepage widgets (rotating images, news, calendar, etc.). Confirm all elements on the homepage work with equal functionality or as re-defined during re-design.
Review Custom Content (Spotlight, top nav, footer). Confirm all Custom Content functions as intended or as re-defined during redesign.
Review the Sitemap for proper configuration – default is 3 levels .
Site Visit Analytics changes – verify that the client has provided us with the Google Analytics code and/or provice client with access to analytics site access if we set it up for them.
If customization(s) had been identified during the initial review stage of the project, identify, understand, & document them in preparation for discussion with the client
Check footer credit.
Review programming specs and verify they are implented as intended.
Check Search page.
HTML: Check page source for Title and Skipnav code.
Check font resizer
Check Login display and functionality
RAD editor font styles
Check Page template edit view
Check Mobile: homepage, interior department (w/banner), interior (w/ side navigation), Interiro (w/o side navigation)
Check browser compatiblity (IE 11, Chrome, Firefox, Edge)
Navigation Responsiveness
Main Navigation Side Navigation Header and Footer